## The team
The team and their roles
The team
| Name | Email | Mobile | Role/Responsibility
| Holly Savin | hollysavin26@gmail.com | 07806 469293 | Scrum master
| Ashley Smith | ashley@goandy.net | 07743 157090 | Lead coder
| Elliott Hill | direct@mrhilster.com | 07940 479887 | Lead designer
|  | Checklist |  |  | done?
Everyone has a copy of all team contact and role details
Everyone is on the Trello project
Everyone has access to shared dropbox folder (containing this file)
Everyone has access to same facebook group
Facebook group is linked to dropbox
We've arranged a time to meetup that suits everyone
Everyone knows who the scrum master is and when the SM should be updated with each teammember's latest schedule
Everyone can access the version repository (assembla.com) - artists may want to version their work or may make separate arrangements to programmers.
Check Box 1
Check Box 1
Check Box 1
Check Box 1
Check Box 1
Check Box 1
Check Box 1
Check Box 1

## Design
What are we making, rough design
Note - alter this content if necessary
One sentence description, if it takes more than that then idea is not clear.
3D racing game
Unique selling points (USPs) - why is the deliverable interesting?
| 1 | Can only score by going fast which is dangerous
| 2 | Handling is simple, but controls feel dynamic
3
4
Concept - what's it going to be like?
| Theme |  | Fantasy, historical, futuristic
| Setting |  | Abstract, Medieval castle, realistic, cartoon
| Genre |  | Architectural, Shooter, platform game, website
| Reference |  | Similar films, books, artwork, games
Concept art / images

## Sprint plan
User stories and sprint planning
Rough idea of how the sprints will fit together
| Activity | Date | Days | Goal description
| Sprint 1 |  | 2 | Very rough version of USPs working | USP - unique selling point, the key features
| Sprint 2 |  | 2 | Minimal working version- crashes, but playable
| Sprint 3 |  | 1 | Final resources and polish for milestone1
| Milestone 1 |  | 1 | Get feedback from real users, formal assessed demo. | Somebody write down what people say, comments from team, etc.
| Final push (sprint4) |  | 1 | Using the demo feedback, what can we fix/improve in the time available?
| Milestone 2 |  | 1 | Gather the power point from the demo, a new trailer video, final Trello screen shots for all sprints. How many hours did everyone work. If there is a disparity, do we need to comment on it? Should everyone get the same mark? Declare any code or assets we didn't make. Hand it all in. Point out to Mark anything you improved since Milestone1.

## User stories
User stories
| Title | Description
Note: one sentence only! These will help generate tasks.

## Schedule
Schedule
Total time on project
| Name | Sprint1 | Sprint2 | Sprint3 | Sprint4(End) | Total hours
| Joe | 1 | 12 | 8 | 0 | 21
| Tim | 3 | 0 | 6 | 3 | 12
| Fred | 0 | 16 | 0 | 0 | 16
| Jane | 8 | 5 | 8 | 1 | 22
| Fez | 5 | 0 | 4 | 3 | 12 | Note: why have Joe and Jane worked nearly twice as much as Tim and Fez? Should they get more marks and Tim/Fez get less?